## Cover
AEGIS
Agentic Penetration-Testing Platform — Business & Technical Requirements (BRD / TRD)
Document | AEGIS BRD/TRD — consolidated requirements, features, integrations, substrates, pentest use cases, MD asks, and XBOW competitive learnings
Program | VM Workshop — greenfield agentic-pentest sandbox
Owner | Enterprise Architecture (horizontal pillar lead)
Version | 0.2 (draft)
Date | 2026-09-22
Scope note | AEGIS runs under its OWN dedicated isolation boundary, operated separately from the Foundation VM platform it reuses.
How to read | Each tab is a register. IDs are stable (BR-, TR-, F-, INT-, SUB-, UC-, DEC-, D-, XB-). The last column of every tab is Comments (tinted) — for your annotations. Live build-status lives in the Design Task Tracker, not here.
Sheet index
0. What We Automate | The one thing named plainly: the exploitability verdict
1. Glossary & Abbreviations | Every keyword and abbreviation (incl. Portico=Kafka/MSK, Bedrock-platform ≠ AWS Bedrock)
2. Business Requirements (BRD) | Business-level requirements incl. the MD's asks
3. Technical Requirements (TRD) | 'Shall' statements — cross-cutting technical requirements
4. Feature Catalog | Every component/capability as a feature, with lane + priority
5. Integrations | External systems AEGIS talks to, direction and protocol
6. Substrates (Reuse vs New) | Reused platform layers vs new AEGIS-owned services
7. Pentest Use Cases | What AEGIS tests, by attack surface (6 surfaces)
8. Design Decisions | Locked decisions (DEC) + open decisions (D)
9. MD Asks & Discussion | The MD discussion list, open questions, inputs needed
10. XBOW Learnings & Parity | Competitive read of XBOW mapped to AEGIS, + items to adopt
11. Architecture Components | The microservices, by plane and lane
12. Open Items / Backlog | The master to-do: design backlog, decisions, research, inputs
13. AWS Infrastructure | AWS services, network tiers, and infrastructure needs (+ capacity/NFRs)
14. Business Outcomes | The value AEGIS delivers, with the metric/KPI for each
15. Requirements (FR/NFR) | Functional + non-functional requirements
16. Architecture Choices | Key design choices, options considered, rationale, trade-offs
17. Volume & Success | Inputs, outputs, total volume, scaling, and the definition of success
18. POC Plan | The POCs to be done — objective, scope, success criteria, dependencies
19. Design Review | Architecture review: 8 findings — issue, why it matters, recommendation, priority

## 0. What We Automate
What We Automate
Name it plainly, before anything else.
AEGIS automates the EXPLOITABILITY VERDICT:
“Is this flagged vulnerability actually exploitable on THIS target, in THIS environment — and prove it?”
Today a human penetration tester makes this judgment by hand: they take a POTENTIAL vulnerability (a CVE/JVE flag, a scanner hit, or a new package), then decide — with reproducible proof — whether it is genuinely exploitable (a true finding) or not (a false positive), on the real target, safely. AEGIS automates that judgment and the work to reach it; a human still reviews and clears the result. Green is earned, never automatic.
Judgments AEGIS automates
# | Judgment automated | What it replaces (done by hand today)
1 | The exploitability verdict (true finding vs false positive) | A pentester manually attempting the exploit to confirm it is real.
2 | Which techniques / tactics to try for a given vuln class | The pentester choosing from their playbook.
3 | Chaining across surfaces (web → cloud metadata → assumed role) | Manual multi-step kill-chain construction (chain depth > 1).
4 | False-positive refutation — is the signal actually real? | The pentester ruling out scanner noise.
5 | Confidence laddering (hypothesis → static → replica_proven → live) | The pentester judging how sure they are.
6 | Evidence capture + a reproducible proof-of-concept | Manual write-up of the repro steps and impact.
7 | (Interactive) how to push harder mid-run | A senior pentester steering the session.
Judgments that STAY human
# | Stays human | Why
1 | Run approval / Rules of Engagement | Authorization is an accountability decision — who sanctioned this test.
2 | Final clear / sign-off (“green is earned”) | A human owns the finding’s disposition.
3 | DESTROY-class / irreversible actions | Risk of harm → human approval + twin only.
4 | Novel exploit synthesis | Gated; not auto-generated.
5 | Scope & target definition | A business / asset-ownership decision.
Boundary — what AEGIS does NOT automate:
• Vulnerability DISCOVERY / scanning — that is the INPUT (Foundation/VINES flags feed AEGIS). • REMEDIATION — that is downstream. AEGIS sits in the middle: it turns ‘flagged’ into ‘proven exploitable / not’, with evidence.

## 1. Glossary
Glossary & Abbreviations
Every keyword and abbreviation. [confirm] = best-effort reading of an internal name (Open Decision D-11).
Term | Category | Meaning | Comments
AEGIS | Platform | The governed agentic pentesting environment — Governance & Planning plus the agentic worker grid.
ARC / ARC-NG | Platform | Internal predecessor / alternate name for the AEGIS agentic pentest platform (seen in the 'ARC-vs-XBOW' analysis).
XBOW | Vendor | Commercial autonomous web-app pentest engine; the competitive benchmark AEGIS aims to beat. Licensed self-hosted pilot at the firm.
VINES | Foundation | VM Ops case app that flags vulnerabilities. [confirm]
Foundation (CTC) | Substrate | Central platform that receives VINES data and emits the headless ExploitabilityRequest.
Portico | Substrate | The Foundation event bus — Kafka on Amazon MSK. (The firm's MSK/Kafka platform is internally named 'Bedrock' — NOT AWS Bedrock.)
Bedrock (MSK platform) | Substrate | The firm's internal name for its MSK/Kafka messaging platform. NOT AWS Bedrock the model service.
Kestra | Substrate | Scheduler that triggers scheduled sweeps (the WHEN). Reused platform trigger, not per-run orchestration.
Cosmos | Substrate | Write-once (Iceberg) store for findings / evidence / audit (WORM).
Mobius | Substrate | VM Ops store consuming the result / VM Risk Score. [confirm input-vs-output path]
Bedrock Mantle | Substrate | In-perimeter model gateway (AWS Bedrock via PrivateLink); standard models now, frontier later.
BB (Bitbucket) | Substrate | Source control / version control.
Artifactory | Substrate | Artifact repository; new packages land here.
Source-of-record repo | Substrate | Git / source of record for cases & agents. [confirm]
Code-authoring agents | Tooling | SmartTask authoring / code-writing agent capability (future). [confirm]
Smart SDK | Tooling | The firm's internal agent SDK/harness layer, built ON TOP OF Google ADK; models served via AWS Bedrock. The AEGIS worker is built on this.
Google ADK | Tooling | Google Agent Development Kit — the agent framework under Smart SDK. Provides the agent loop (Runner), tools, and a code-executor abstraction.
LiteLlm | Tooling | ADK's adapter to non-Gemini providers; how AEGIS reaches Claude-on-Bedrock (model string 'bedrock/anthropic.claude-...').
Plexus | Tooling | Internal n8n fork; governed drag-and-drop playbook composition for CyberOps (future scale-out, not Phase-0).
SID | Identity | Human identity established at login (SSO / ADFS / OIDC).
FID | Identity | Functional ID; the per-run least-privilege workload identity minted by the orchestrator.
OBO | Identity | On-behalf-of; console-api carries the human SID to the orchestrator when creating a run.
RoE | Governance | Rules of Engagement — scope, windows, permitted techniques. A run is admitted only under a valid RoE.
change ticket | Governance | Change ticket / change-management gate for ad-hoc & interactive runs. [confirm]
Action-class | Governance | READ (allow) · CHANGE (approval/replica) · DESTROY (twin only) · UNKNOWN (default-deny).
Governance | Governance | External authorization wall — authorize(action) on every action, fail-closed; lives OUTSIDE the runtime (via Run Broker).
Guardrails | Governance | Soft, in-runtime content hygiene (prompt-injection filter in / output sanity out). NOT a security boundary; never a substitute for governance.
Run Broker | Component | Single inward reverse-proxy; the worker's ONLY control-plane door. Worker has exactly 2 outbound paths (Run Broker + Egress-gateway).
Egress-gateway | Component | The single scoped exit; the only route out of the task tier to targets. Enforces URL/DNS scope + per-target rate limit.
Validator | Component | Independent service that re-proves a proposed finding (refute-by-default). The ONLY writer of findings.
Confidence ladder | Concept | hypothesis → static → replica_proven → live_confirmed. Only the Validator advances a rung; the agent only proposes.
Prod-safe zones | Concept | A = read-only prod discovery · B = replica exploitation · C = gated prod confirmation (human-approved).
Twin / replica | Concept | Isolated replica environment for destructive (DESTROY-class) testing. Zone B.
Case | Data | The durable 'question' — is vuln X exploitable on target Y? Persists across attempts.
Run | Data | One attempt against a Case. Retries / interactive sessions are new Runs under the same Case.
ExploitabilityRequest / Result | Data | Inbound machine request (from Foundation via Portico) / outbound verdict contract (to Mobius).
Idempotency-Key | Data | Client-generated dedup key required on POST /runs (24h TTL, stored in Foundation Postgres). Same key → same run.
WORM | Concept | Write-once-read-many — tamper-evident audit. Evidence/findings/audit are hash-chained WORM in Cosmos.
SSE | Protocol | Server-Sent Events — the live run stream to the human console. (WebSocket revisited when interactive is built.)
Firecracker | Isolation | AWS microVM (hypervisor boundary) — the baseline worker isolation, because the worker runs exploit code.
Fargate | Isolation | AWS managed compute that runs the Firecracker microVM.
gVisor | Isolation | Kernel-level sandbox; fallback isolation if forced onto plain containers.
udocker | Isolation | Rootless container packaging option — NOT the security boundary.
OOB / OAST | Technique | Out-of-band (application security testing) — a callback path the target reaches back to, to prove SSRF / blind vulns.
interactsh | Tooling | An OOB/OAST callback server (XBOW uses one). AEGIS gap L7.5 — the target-return path.
Coverage map | Concept | endpoint × attackType matrix with a 4-state status (TESTED_EXHAUSTIVELY / TESTED / UNTESTED_ATTRACTIVE / UNTESTED). XBOW-inspired; AEGIS to adopt.
CP | Abbrev | Control Plane.
CVE / JVE / CWE | Abbrev | Public / internal vuln identifiers / weakness taxonomy.
DLQ | Abbrev | Dead-Letter Queue (for poison / malformed events).
VM Risk Score | Metric | VM Ops score that the exploitability verdict feeds.
A/B champion-challenger | Concept | Model/agent promotion gate: a challenger must beat the champion on the eval benchmark to be promoted.
Quartermaster / Larch | Ref (XBOW) | XBOW's per-run infra provisioner / orchestration-API (for comparison only; not AEGIS terms).
Parrot | Ref (XBOW) | XBOW's egress gateway (mitmproxy + dnsdist) enforcing URL/DNS scope + RPS (comparison only).

## 2. BRD
Business Requirements (BRD)
Business-level requirements, including the MD's asks.
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Requirement | Detail | Pri | Source | Comments
BR-1 | Governed in-house build | Build a governed, in-house agentic pentest sandbox to retain offensive capability (vs buy/cede). | P0 | MD / D-1 (opt a)
BR-2 | Two populations | Support two populations: a platform-owned stable BASELINE (runs by default) and CyberOps INTERACTIVE (ad-hoc exploit code, PR-promoted into baseline). | P0 | MD ask A
BR-3 | Concurrent runs | Baseline runs on every target concurrently; interactive runs alongside on the SAME target without stopping the others. | P0 | MD
BR-4 | Attribution | Every run is governed and attributable — no ungoverned action; human SID → per-run FID stamped on every logged action. | P0 | MD concern #2
BR-5 | Sandboxed | Execution is sandboxed — security is the #1 concern; the worker runs exploit code and needs a real isolation boundary. | P0 | MD concern #1
BR-6 | Change management | Ad-hoc / interactive runs go through change management (change ticket). | P1 | MD
BR-7 | Human-in-the-loop | A human clears findings; 'green' (cleared) is earned by review, never automatic. | P0 | design
BR-8 | Result destination | Findings feed the VM Risk Score / Mobius via a clean ownership boundary (sandbox returns; VM Ops persists). | P1 | D-5 (opt b)
BR-9 | Success bar | POC success bar: false-positive rate < 1%, N proven findings = [TBD], cost per proven finding ≤ [TBD]. | P0 | D-12 / MD | Needs MD input (numbers).
BR-10 | Isolation boundary | AEGIS lands under its OWN dedicated isolation boundary, operated separately from the Foundation platform it reuses. | P0 | stated
BR-11 | Beat XBOW | Exceed XBOW on the axes XBOW lacks: twin/replica re-prove, human↔agent identity binding, and non-web attack surface. | P1 | strategy
BR-12 | POC directions | Evaluate three POC directions: (1) build pipeline, (2) sandbox idea, (3) on-prem. | P1 | MD
BR-13 | Break-glass | Break-glass: default NONE — confirm the MD agrees there is no bypass. | P0 | D-8 | Needs explicit MD decision.
BR-14 | Malware scope | Malware: contained detonation / analysis only (never generation); twin/isolated; CyberOps + Review owned; DESTROY-class. | P1 | D-9
BR-15 | Reuse substrates | Reuse platform substrates — no new database, no new bus, no Redis. | P0 | design
BR-16 | Regulated audit | Maintain a regulated-audit posture: WORM tamper-evident evidence, and a standards backbone (PTES/OWASP/NIST/MITRE/DORA/PCI). | P0 | design
BR-17 | MD open questions | Resolve the 3 starred questions the MD raised in the discussion. | P0 | MD | 3 starred questions — text TBD from MD.
BR-18 | Coverage & continuity | Continuous coverage — measure % of flagged vulns proven; sweep on a cadence (Kestra). | P1 | design

## 3. TRD
Technical Requirements (TRD)
Cross-cutting 'shall' statements. Component-level detail is in the Feature Catalog and Architecture Components tabs.
ID | Requirement (SHALL) | Area | Pri | Comments
TR-1 | Runs SHALL be async fire-and-stream: POST /runs returns run_id (202) immediately; progress via SSE or poll. Never block for a verdict. | Run model | P0
TR-2 | There SHALL be two edge services by caller type — console-api (humans; REST+SSE) and intake (machines; Portico consumer, idempotent). Never merged. | Entry | P0
TR-3 | Edges SHALL be thin and stateless — no pentest logic, no target access, no standing secrets. | Entry | P0
TR-4 | All internal communication SHALL be HTTPS only (no gRPC) with mTLS + per-service workload identity. | Platform | P0
TR-5 | Commands-needing-an-answer = sync HTTPS; 'this happened' facts = Portico events; live UI updates = SSE. | Platform | P0
TR-6 | Governance SHALL be external to the runtime (reached via the Run Broker), never in-process in the agent. | Governance | P0
TR-7 | The worker SHALL have exactly two outbound paths: the Run Broker (control-plane) and the Egress-gateway (targets). | Runtime | P0
TR-8 | Every action SHALL be action-classed (READ/CHANGE/DESTROY/UNKNOWN) and authorize()-gated; UNKNOWN is default-deny. | Governance | P0
TR-9 | Guardrails (content hygiene) SHALL NOT substitute for governance (the action-authorization wall). | Governance | P0
TR-10 | Baseline worker isolation SHALL be a Firecracker microVM (via Fargate); gVisor is the fallback; udocker is packaging only. | Runtime | P0
TR-11 | Model-generated code SHALL execute INSIDE the per-run microVM via a custom ADK BaseCodeExecutor (classify → authorize → ship → record); the worker process never exec()s code. | Runtime | P0
TR-12 | Identity: human SID (SSO/OIDC) carried on-behalf-of; per-run FID; both on every logged action; a run with no SID SHALL be refused. | Identity | P0
TR-13 | POST /runs SHALL require an Idempotency-Key (24h TTL, Postgres store); intake SHALL dedup on the event id via a transactional outbox. | Entry/Backbone | P0
TR-14 | All 4xx/5xx SHALL return the standard error envelope {error, code, request_id}. | Entry | P0
TR-15 | Rate limiting SHALL be 2 layers: edge throttle (per-SID) + admission/concurrency (per target+env, platform-wide). Over-limit → 429 + Retry-After. | Entry/Control | P0
TR-16 | Every run SHALL be approved under a valid RoE before admission — baseline runs included (standing engagement). | Governance | P0
TR-17 | The Egress-gateway SHALL be the single scoped door — URL/DNS scope-check + per-target rate-limit, reading the run's RoE. | Egress | P0
TR-18 | Prod-safe zones A/B/C SHALL route by action-class; Zone B provisions a replica; Zone C is gated + human-approved. | Egress | P0
TR-19 | Findings SHALL be written ONLY by the Validator (refute-by-default), advancing the confidence ladder. | Control | P0
TR-20 | Evidence / findings / audit SHALL be hash-chained WORM in Cosmos (Iceberg), pointer-only. | Data | P0
TR-21 | State SHALL reuse Foundation Postgres (state) + Cosmos (WORM). No new DB, no Redis. | Data | P0
TR-22 | The event backbone SHALL be Portico (Kafka/MSK); reliable emit via a transactional outbox; DLQ + retry for poison/malformed events. | Backbone | P0
TR-23 | Kestra SHALL be trigger-only (sweeps / SLA timers); the orchestrator is our own per-run control-plane service (route → plan → spawn → track). | Backbone/Control | P0
TR-24 | Model access SHALL go via the model-port over Smart SDK/ADK → Bedrock (LiteLlm), with per-call budgets + prompt elision, model fallback, and graceful handling of firm-proxy request-size/frequency limits. | Runtime | P1
TR-25 | The kill-switch SHALL reach a LIVE worker (not DB-only); a lease dead-man switch SHALL abort on expiry. | Rails/Control | P0
TR-26 | The cred-vendor SHALL issue short-lived, scoped FID credentials per run. | Control | P0
TR-27 | The coordinator SHALL enforce per-target rate limits and collision avoidance across concurrent runs. | Control | P1
TR-28 | A cost rail SHALL enforce a per-run budget (token / time / action accounting) and cut off on breach. | Rails | P1
TR-29 | Observability SHALL propagate a trace/correlation id request→run→action, and track model_refusal as an operational friction (XBOW learning). | Rails | P1
TR-30 | A governed, in-scope target-return / OOB callback path SHALL exist to prove SSRF and blind vulns (without opening a hole in the sandbox). | Egress | P1
TR-31 | A coverage map (endpoint × attackType, 4-state) SHALL be tracked and included in the result (XBOW learning). | Control/Output | P1
TR-32 | Resilience: circuit breakers, timeouts, backpressure and retry budgets SHALL be defined per hop. | Rails | P1

## 4. Features
Feature Catalog
Every component/capability as a feature, with lane and priority.
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Feature | Lane | Description | Pri | Comments
F-01 | console-api (human edge) | L1 | Async REST + SSE front door; endpoints, idempotency, error envelope, SSE stream + reconnect. | P0
F-02 | intake (machine edge) | L1 | Portico event consumer; idempotent; case-owner stamping. | P0
F-03 | TLS + platform LB | L1 | Front door for internal callers; TLS/mTLS boundary. | P1
F-04 | AuthN/AuthZ (RBAC) | L1 | OIDC→SID, on-behalf-of, who-can-start-what. | P0
F-05 | Validate (schema) | L2 | ExploitabilityRequest schema + RoE-ref check. | P0
F-06 | Case model (normalize) | L2 | Canonical Case schema; CVE/JVE/CWE canonicalization. | P0
F-07 | Dedup / idempotency | L2 | SHA-256 fingerprint, Postgres store, 409 conflict. | P0
F-08 | Classify & route (AI) | L2 | Vuln → surface + case(s) + zone policy. | P0
F-09 | Create Case + emit | L2 | Create case, index, emit run.accepted (outbox). | P0
F-10 | Quarantine | L2 | Hold + replay for invalid/unmapped. | P1
F-11 | Portico topics/contract | L3 | exploitability.request, run.*, agent.*, findings.*, audit.*. | P0
F-12 | Reliable emit (outbox) | L3 | Transactional publish / exactly-once at run creation. | P0
F-13 | DLQ + retry | L3 | Backoff, poison-pill, human replay. | P1
F-14 | Orchestrator | L3 | Case router + run planner (NOT a saga engine). | P0
F-15 | Kestra triggers | L3 | Scheduled sweeps + SLA timers (trigger only). | P1
F-16 | Governed agent loop | L4 | plan→authorize→act→observe→reflect→propose (ADK Runner). | P0
F-17 | Run Broker | L4 | Single reverse-proxy; all CP calls; audit boundary. | P0
F-18 | Agent memory/context | L4 | Working memory + context budget + summarization (ADK/Smart SDK). | P1
F-19 | Tool registry / action classifier | L4 | Allow-listed, action-classed tools; per-tool timeout. Real classifier still to build. | P0
F-20 | Model-port | L4 | LiteLlm→Bedrock; budgets, elision, fallback, proxy-limit handling. | P1
F-21 | Worker isolation | L4 | Golden image, FID, no-internet-route; Firecracker microVM + guest agent. | P0
F-22 | Interactive / HITL | L4 | Author instructions, live steer, sign-off. | P1
F-23 | Governance authorize() | L5 | authorize(action,ctx); action-class × RoE; fail-closed; kill. | P0
F-24 | Cred-vendor | L5 | Short-lived FID creds, scoping. | P0
F-25 | Lease-controller | L5 | Dead-man switch, renewal, expiry→abort. | P0
F-26 | Coordinator | L5 | Per-target rate + collision avoidance. | P1
F-27 | Validator | L5 | Re-prove, confidence ladder, only-writer-of-findings, adversarial refute. | P0
F-28 | Evidence-audit | L5 | Hash-chained WORM, pointer-only. | P0
F-29 | Foundation Postgres schema | L6 | case/run/lease/state/idempotency tables. | P0
F-30 | Cosmos (Iceberg) schema | L6 | findings/evidence/audit/index (write-once). | P0
F-31 | Bedrock Mantle access | L6 | Model gateway via PrivateLink. | P1
F-32 | Knowledge graph / vector memory | L6 | Proven-paths → improve future runs (future). | P2
F-33 | Egress-gateway | L7 | The one door; scope-check + rate-limit; reads RoE. | P0
F-34 | Prod-safe zones A/B/C | L7 | Routing + replica provisioning + canary gate. | P0
F-35 | Targets & network | L7 | dev/test/UAT/prod segmentation (D-2). | P0
F-36 | Result composer + outbound | L7 | ExploitabilityResult, report, → Mobius. | P1
F-37 | Target-return / OOB callback | L7 | SSRF / blind-vuln verification listener (XBOW learning). | P1
F-38 | Identity rail | L8 | SID→FID, session tags, no-SID-refuse, CloudTrail+Cosmos. | P0
F-39 | Resilience rail | L8 | Circuit breakers, timeouts, backpressure, retry budgets. | P1
F-40 | Rollback/compensation rail | L8 | Partial-run compensation, idempotent undo. | P1
F-41 | Observability rail | L8 | Trace/correlation-id; metrics; SLOs; model_refusal metric. | P1
F-42 | Cost rail | L8 | Per-run budget enforcement; token/time/action accounting. | P1
F-43 | Kill-switch / config rail | L8 | Cancel reaching a live worker; feature flags. | P0
F-44 | Learning rail / eval harness | L8 | FP<1% gate; A/B champion-challenger; coverage map. | P1
F-45 | Ops rail | L8 | Live monitoring, SOC deconfliction, target cleanup/reconciliation. | P1
F-46 | Web console (SPA) | UI | Production React console on the console-api (dashboard, runs, run detail w/ SSE, findings). | P1

## 5. Integrations
Integrations
External systems AEGIS talks to. Reuse/New tells you what's existing vs to be built.
ID | System | Type | Direction | Protocol | Purpose | Reuse/New | Comments
INT-01 | Portico (Kafka / MSK) | Event bus | In & Out | Kafka / MSK | intake consumes ExploitabilityRequest; run.*, agent.*, findings.*, audit.* events published. | Reuse
INT-02 | Kestra | Scheduler | Trigger | platform | Fires scheduled sweeps and SLA timers (the WHEN). | Reuse
INT-03 | Foundation Postgres | Datastore | Read/Write | SQL | case / run / lease / state / idempotency-key store. | Reuse
INT-04 | Cosmos (Iceberg) | Datastore (WORM) | Write | Iceberg | findings / evidence / audit — write-once, hash-chained. | Reuse
INT-05 | Bedrock Mantle / AWS Bedrock | Model gateway | Out | HTTPS / PrivateLink | Model inference via Smart SDK / ADK / LiteLlm (Claude-on-Bedrock). | Reuse
INT-06 | Mobius | Datastore | Out | contract | ExploitabilityResult / VM Risk Score consumed by VM Ops. | Reuse
INT-07 | VINES / Foundation (CTC) | Upstream | In | Portico event | Source of the headless ExploitabilityRequest. | Reuse
INT-08 | IdP / ADFS (OIDC) | Auth | In | OIDC / PKCE | SID / SSO for the human console; on-behalf-of to orchestrator. | Reuse
INT-09 | BB / Artifactory / source repo | SCM / artifacts | In | Git / repo | Baseline code, PR promotion of interactive code, new-package trigger. | Reuse
INT-10 | Smart SDK / Google ADK | Agent framework | Embed | SDK | The worker harness, agent loop, and code executor. | Reuse / build
INT-11 | Egress targets (dev/test/UAT/prod) | Targets | Out | HTTPS via gateway | The systems under test — reached ONLY through the egress-gateway. | External
INT-12 | Twin / replica environment | Targets | Out | provisioned | Zone B destructive testing on an isolated replica. | Build
INT-13 | OOB / OAST callback listener | OOB | In | callback | SSRF / blind-vuln verification (interactsh-style). NEW capability. | New
INT-14 | SIEM / CloudTrail | Observability | Out | logs | Audit + attribution trail (identity rail). | Reuse

## 6. Substrates
Substrates — Reuse vs New
What AEGIS reuses from the platform vs what it builds new (under its own dedicated account).
ID | Substrate / Layer | Owner | Reuse/New | What AEGIS uses it for | Notes | Comments
SUB-01 | Portico (Kafka/MSK) | Foundation | Reuse | Event backbone — request intake + run/agent/findings/audit events. | The firm's MSK platform ('Bedrock' name). No new bus.
SUB-02 | Foundation Postgres | Foundation | Reuse | Durable state — case/run/lease/idempotency. | No new relational DB.
SUB-03 | Cosmos (Iceberg) | Foundation | Reuse | WORM store — findings/evidence/audit. | Tamper-evident, pointer-only.
SUB-04 | Bedrock Mantle | Foundation | Reuse | In-perimeter model gateway (AWS Bedrock). | Standard now, frontier later.
SUB-05 | Kestra | Foundation | Reuse | Scheduled triggers (sweeps/SLA). | Trigger only, not orchestration.
SUB-06 | Foundation VM platform (CTC/VINES) | Foundation | Reuse | Upstream vuln flags + ExploitabilityRequest. | Handoff contract TBD.
SUB-07 | BB / Artifactory / source repo | Foundation | Reuse | Source control, artifacts, case/agent source of record. | Baseline + PR promotion path.
SUB-08 | IdP / ADFS (OIDC) | Enterprise | Reuse | Human identity (SID) / SSO. | On-behalf-of to orchestrator.
SUB-09 | Smart SDK / Google ADK | Enterprise | Reuse + build | Agent framework the worker is built on. | Configure a harness, not build a loop.
SUB-10 | AEGIS control plane | AEGIS (own account) | New | orchestrator, governance, run-broker, cred-vendor, lease-controller, coordinator, model-port, validator, evidence-audit, egress-gateway. | Deterministic services; the governed wall.
SUB-11 | AEGIS edges | AEGIS (own account) | New | console-api (humans) + intake (machines). | Thin, stateless.
SUB-12 | AEGIS runtime | AEGIS (own account) | New | Per-run disposable worker (Firecracker microVM + guest agent). | Runs exploit code; hypervisor boundary.

## 7. Use Cases
Pentest Use Cases
What AEGIS tests, by attack surface. Designed by pattern: a case = a spec line, not new governance code. Zone: A=read-only prod · B=replica · C=gated prod.
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Surface | Family | Representative cases | Action-class | 'Proven' means | Zone | Comments
UC-01 | 1 · Web App & API | Information gathering | fingerprint, config exposure, metafiles | READ | exposed artefact captured | A
UC-02 | 1 · Web App & API | Config & deploy mgmt | headers, TLS, default creds, admin panels | READ/CHANGE | reproduced weak config | A/B
UC-03 | 1 · Web App & API | Identity & auth (ATHN) | weak login, MFA gaps, credential stuffing (throttled) | CHANGE | auth bypass reproduced on replica | B
UC-04 | 1 · Web App & API | Authorization (ATHZ) | IDOR/BOLA, priv-esc, path traversal | READ/CHANGE | accessed out-of-scope object | A/B
UC-05 | 1 · Web App & API | Session (SESS) | fixation, weak tokens, CSRF | CHANGE | session takeover on replica | B
UC-06 | 1 · Web App & API | Input validation (INPV) | SQLi, XSS, SSTI, command injection | CHANGE/DESTROY | payload → sink with differential | B / twin
UC-07 | 1 · Web App & API | Business logic (BUSL) | workflow abuse, race conditions | CHANGE | logic broken on replica | B
UC-08 | 1 · Web App & API | API Top 10 | BOLA, broken auth, SSRF, mass-assignment, injection | READ/CHANGE | reproduced request/response + differential | A/B
UC-09 | 1 · Web App & API | Protocols | JWT/OAuth/OIDC/SAML, GraphQL, SOAP, gRPC | CHANGE | token/authz abuse reproduced | B
UC-10 | 1 · Web App & API | Advanced chains | request smuggling, cache poisoning, deserialization, upload→RCE, SSRF chains | CHANGE→DESTROY | full chain proven on twin | B / twin
UC-11 | 2 · Network/Infra/AD | External attack surface | subdomain/asset discovery, exposed services, VPN/RDP/Citrix | READ | in-scope asset + exposure captured | A
UC-12 | 2 · Network/Infra/AD | Service testing | SMB signing, LDAP anon-bind, DNS AXFR, SMTP relay, DB defaults | READ/CHANGE | reproduced weakness | A/B
UC-13 | 2 · Network/Infra/AD | AD identity abuse | Kerberoast, AS-REP roast, delegation, ADCS ESC1-16 | CHANGE | path to Domain Admin in replica | B (twin)
UC-14 | 2 · Network/Infra/AD | Relay / coercion | NTLM relay, PetitPotam/PrinterBug/DFSCoerce | CHANGE→DESTROY | relay path proven on replica only | B (twin)
UC-15 | 3 · Cloud/Container/K8s | IAM & identity | over-privileged roles, assumable roles, key exposure | READ/CHANGE | assumed role / reached resource | A/B
UC-16 | 3 · Cloud/Container/K8s | Metadata & SSRF | IMDS access, metadata exfil | CHANGE | credentials reached via metadata (replica) | B
UC-17 | 3 · Cloud/Container/K8s | Container / K8s | RBAC, privileged pods, escape paths | CHANGE→DESTROY | escape proven on replica cluster | B
UC-18 | 4 · Mobile/IoT/OT | Mobile (MASTG) | storage, transport, auth, hardening | READ/CHANGE | replica/instrumented | lab
UC-19 | 4 · Mobile/IoT/OT | IoT / firmware | firmware extract, UART/JTAG, companion app | READ/CHANGE | lab only | lab
UC-20 | 4 · Mobile/IoT/OT | OT / ICS | OFF by default — specialist safety regime, twin/lab only | — | safety-first | lab/twin
UC-21 | 5 · Red Team / Purple | Adversary emulation | agent-assisted, human-led objective under signed RoE | mixed | objective reached under RoE | mixed
UC-22 | 5 · Red Team / Purple | Social engineering | human-led; agent drafts, human sends | CHANGE | strict authorization gates | —
UC-23 | 5 · Red Team / Purple | Purple teaming | agent replays ATT&CK with blue team | READ/CHANGE | detection improvement measured | A/B
UC-24 | 6 · AI / LLM / Agentic | Prompt injection | untrusted content → instruction | — | traced source→consequential sink | stat
UC-25 | 6 · AI / LLM / Agentic | Excessive agency | injection → action (RCE, exfil) | — | action attributable to injected input | stat
UC-26 | 6 · AI / LLM / Agentic | Sandbox escape | code-exec agents reach host/metadata | — | code escapes sandbox | stat
UC-27 | Cross-surface | Chain (the moat) | web SSRF → cloud metadata → assumed role → data store | READ→CHANGE→DESTROY | chain depth > 1 proven | A→B→twin
UC-28 | Contained | Malware | contained detonation / analysis only (never generation) | DESTROY | twin/isolated; CyberOps+Review owned | twin

## 8. Decisions
Design Decisions
DEC-* are locked; D-* are open. State + rationale are in the note column.
ID | Decision | Note | Comments
DEC-1 | Governance is EXTERNAL to the runtime (via Run Broker), never in-process. | Locked. A compromised agent can't bypass/forge/silence its own guard.
DEC-2 | Run Broker is a CONTROL-PLANE service (single inward reverse-proxy). | Locked. Collapses 7 CP deps into 1 governed door; worker has exactly 2 outbound paths.
DEC-3 | Guardrails ≠ Governance (soft content hygiene vs hard action wall). | Locked. Never let a guardrail stand in for governance.
DEC-4 | Kestra = trigger only; orchestrator = our per-run control-plane service. | Locked. Kestra is the WHEN, not the WHAT/HOW.
DEC-5 | Baseline worker isolation = Firecracker microVM (Fargate), not plain Docker. | Locked. Worker runs exploit code → needs a hypervisor boundary.
DEC-6 | console-api = async fire-and-stream (202 + run_id). | Locked. Runs take minutes-to-hours; never block for a verdict.
DEC-7 | Live stream = SSE now, WebSocket later. | Locked. Progress is one-directional; SSE is proxy-friendly + auto-reconnecting.
DEC-8 | Idempotency-Key required on POST /runs (24h TTL, Postgres). | Locked. Double-click / retry must not launch two runs.
DEC-9 | console-api creates the run via a direct sync HTTPS call to the orchestrator. | Locked. Human path needs an immediate run_id; event path is the machine intake door.
DEC-10 | Standard error envelope {error, code, request_id} on all 4xx/5xx. | Locked.
DEC-11 | Every run is approved (valid RoE) — baseline included. | Locked. 'Baseline' = no human steering, NOT approval-free.
DEC-12 | Rate limit = 2 layers (edge throttle + admission/concurrency). | Locked.
DEC-13 | Worker = a harness on Google ADK + Smart SDK; models via Bedrock; custom BaseCodeExecutor into the microVM. | Locked. ADK gives the loop + code-executor socket; AEGIS supplies the safe plug.
D-1 | Build in-house vs buy vs cede → recommend (a) governed in-house build. | Open — MD. Retain governed offensive capability.
D-2 | Network isolation for dev/test/UAT (share PROD net) — full seg vs twin vs egress-only interim. | BLOCKED — the load-bearing decision; owner @network-lead.
D-3 | Headless RoE model — standing envelope vs per-request sign-off. | Open. Recommend standing envelope; per-request for CHANGE+.
D-4 | Headless accountability — service principal + named case-owner attribution. | Open.
D-5 | Result destination — sandbox writes Mobius vs returns via contract. | Open. Recommend (b): clean ownership boundary.
D-6 | Runtime — now decided as Firecracker microVM/Fargate (see DEC-5). | Ready to close as DECIDED.
D-7 | Console UI ownership — CLI now → UI on the API later. | Open. A prototype React console now exists; owner TBD.
D-8 | Break-glass — none, or emergency override? | Open — MD. Was dropped; needs an explicit call.
D-9 | Malware scope — contained detonation only, twin, CyberOps+Review owned. | Open. DESTROY-class.
D-10 | Twin availability per target — which targets get a replica, and how. | Open. Replicable web/API first.
D-11 | Confirm internal naming — incl. Portico = Kafka/MSK, platform 'Bedrock' ≠ AWS Bedrock. | Open. Before external circulation.
D-12 | POC success bar — FP<1%, N proven [TBD], cost/finding [TBD]. | Open — MD. Needs numbers.

## 9. MD Asks
MD Asks & Discussion
The MD discussion list (from the two photos) + open questions. ★ = starred by the MD.
ID | Topic | Ask / note | Comments
MD-01 | Ops capabilities | What can CyberOps do? configuration (devspace), headless FID agents (udocker), source-controlled eng path, CLI tool, source repo→Git, Claude Code path. | Captured.
MD-02 | Concern #1 — Security | Execution must be sandboxed. | Captured (DEC-5).
MD-03 | Concern #2 — Identity | SID vs FID — 'SID on VDI → rules → sandbox'; human SID → per-run FID. | Captured (identity rail).
MD-04 | Flow | SDLC → new package → Portico (events) → Kestra → sandbox. | Captured.
MD-05 | Mobius path | Notes put Mobius on the INPUT path (Portico → mobius → sandbox); deck shows it as future output. | Confirm which is correct.
MD-06 | Egress | One door out (egress-gateway). | Captured.
MD-07 | Base image | Golden pentest base image + fork per sandbox. | Captured.
MD-08 | Modes | Headless/baseline (auto, HITL, bindings) + interactive (+SID +AI, red team). | Captured.
MD-09 | Change mgmt | Ad-hoc → change-managed (change ticket); interactive mode. | Open.
MD-10 | Break-glass | Present in notes; deliberately dropped. | Needs MD decision (D-8).
MD-11 | POC directions | (1) build pipeline (2) sandbox idea (3) on-prem; VP-level, many-on-sandbox, 1 post-release. | Open.
MD-12 | Stakeholders (roles only) | Head of Pentesting (the ask went to this role), Exploitability / exploit-agent lead, VM Process owner, Ops-capabilities owner. | Names removed — refer to roles.
MD-13 | Tooling terms | internal team platform, SmartSDK, code-authoring agents, VT harness, Artifactory/bb-acctest, 'Sandboxing Pact', chains of orchestration. | Confirm (D-11).
MD-14 | ★ Question 1 | [TBD — transcribe the first starred MD question] | Needs MD.
MD-15 | ★ Question 2 | [TBD — transcribe the second starred MD question] | Needs MD.
MD-16 | ★ Question 3 | [TBD — transcribe the third starred MD question] | Needs MD.
MD-17 | Business case [TBD] | Volumes and cost/finding placeholders — needed to close D-12. | Needs MD.

## 10. XBOW Learnings
XBOW Learnings & AEGIS Parity
Competitive read of XBOW (documentation-only, from the licensed pilot) mapped to AEGIS. Verdict: ADOPT / MATCH / AEGIS-ahead.
ID | Dimension | XBOW (what it does) | AEGIS position | Verdict / action | Comments
XB-01 | Recon & discovery | Live-site + source-code discovery agents; endpoint hunting; WAF fingerprint; coverage map (endpoint×attackType, 4-state). | AEGIS has recon; NO explicit coverage map. | ADOPT coverage map
XB-02 | Vuln classes | 38-class web taxonomy + 43 tactics; CWE mapping explicit; OWASP partial; WSTG/PTES not structured. | AEGIS covers web + network/AD/cloud/mobile/AI (broader). | AEGIS ahead (surface)
XB-03 | Proof / exploitation depth | Detection ≠ demonstration; reproduced-in-trace; script-verified re-runnable PoC; proof-contract (passed/failed/ambiguous). | AEGIS Validator + confidence ladder; must match rigor. | MATCH + store re-runnable PoC
XB-04 | Twin / replica re-prove | NONE — reproduces in-trace only. | AEGIS re-proves on a Zone-B replica (replica_proven rung). | AEGIS ahead
XB-05 | Validation / FP | 3-stage adversarial cascade + FP-family taxonomy + voting quorum. | AEGIS Validator refute-by-default; adopt adversarial stage + FP families. | ADOPT adversarial FP cascade
XB-06 | Reporting | Finding JSON schema; report doc (exec summary, methodology, states); Prince PDF; human attestation. | AEGIS result composer + report; align schema. | MATCH
XB-07 | Scope & RoE | Parrot egress (mitmproxy+dnsdist); URL/DNS scope; SIGNED x-param anti-scope-drift; command-safety vetting. | AEGIS egress-gateway + governance; adopt signed anti-drift prefix. | ADOPT signed prefix
XB-08 | Rate / stability | Fixed-window RPS at egress; back-pressure queue; AGENT BACK-OFF message on limit; stability frictions. | AEGIS coordinator + egress; adopt back-off message. | ADOPT back-off msg
XB-09 | Model usage | 37 model configs; Bedrock AssumeRole; per-call BUDGETS + prompt ELISION; tiered token pricing; fallback. | AEGIS model-port is thinner; adopt budgets/elision. | ADOPT budgets/elision
XB-10 | Deployment | K8s per-ExperimentRun CR + operator; Debian attack image (root, sshd+supervisord); interactsh OOB. | AEGIS = Firecracker microVM (stronger isolation); confirms OOB need. | AEGIS ahead (isolation)
XB-11 | Credits / cost | Internal token-cost accounting; customer credit ledger = SaaS (not observed). | AEGIS cost rail (per-run budget); attack-credits ≈ our budget unit. | MATCH (cost rail)
XB-12 | Operability | Metrics/OTel/Sentry; trace extract; record/replay; nudge course-correction; staff-only debug. | AEGIS observability rail; we own our debug tooling. | MATCH
XB-13 | Identity / tracing | Agent attribution + provenance on findings; per-run K8s SAs; NO human↔agent (SID→FID) binding. | AEGIS binds every action to a named human (SID→FID). | AEGIS ahead (attribution)
XB-14 | Model refusal | Tracked as an operational friction ('moralizing / watering down a PoC'); never shown to customer. | AEGIS should track model_refusal as a metric too. | ADOPT model_refusal metric
XB-15 | Failure taxonomy | 51 friction subtypes across 6 categories (auth/coordination/infra/scope/target/other). | Feeds AEGIS resilience + ops-readiness lists. | ADOPT friction taxonomy
XB-16 | Capability boundary | WEB-ONLY — no network/AD/binary/wireless/phishing classes. | AEGIS multi-surface by design. | AEGIS ahead

## 11. Components
Architecture Components
The AEGIS microservices by plane and lane, plus reused substrates.
Component | Plane | Lane | Role | Comments
console-api | Edge | L1 | Human REST+SSE front door.
intake | Edge | L1 | Machine Portico consumer, idempotent.
orchestrator | Control plane | L3 | Case router + per-run planner (not a saga).
governance | Control plane | L5 | authorize(action) external wall; action-class × RoE.
run-broker | Control plane | L4 | Single inward reverse-proxy; the worker's only CP door.
cred-vendor | Control plane | L5 | Short-lived scoped FID credentials.
lease-controller | Control plane | L5 | Dead-man switch; renewal; expiry→abort.
coordinator | Control plane | L5 | Per-target rate + collision avoidance.
model-port | Control plane | L4 | Model access via Smart SDK/ADK→Bedrock; budgets/fallback.
validator | Control plane | L5 | Re-prove; confidence ladder; only writer of findings.
evidence-audit | Control plane | L5 | Hash-chained WORM; pointer-only.
egress-gateway | Control plane | L7 | The one door out; scope-check + rate-limit.
worker (per-run) | Runtime | L4 | Disposable Firecracker microVM; agent core + clients; runs as FID.
guest-agent | Runtime | L4 | In-microVM code executor (receives + runs generated code).
Portico | Substrate | L3 | Kafka/MSK event backbone (reused).
Foundation Postgres | Substrate | L6 | Durable state (reused).
Cosmos (Iceberg) | Substrate | L6 | WORM findings/evidence/audit (reused).
Bedrock Mantle | Substrate | L6 | Model gateway (reused).
Kestra | Substrate | L3 | Scheduled triggers (reused).

## 12. Backlog
Open Items / Backlog (Master TO-DO)
The consolidated to-do: design backlog (A), decisions (B), research (C), inputs from you (D), and the 8 XBOW items to adopt.
ID | Track | Item | Pri | Comments
A1 | Design backlog | Governance authorize() spec (L5.1) | P0 | Next — worker already calls it.
A2 | Design backlog | Case model (L2.2) — canonical schema + Case-vs-Run + dedup | P0 | Keystone data model.
A3 | Design backlog | Portico topics + event schemas (L3.1) | P0 | The Kafka contract.
A4 | Design backlog | AuthN/AuthZ RBAC (L1.4) | P0 | Gates console-api.
A5 | Design backlog | Real action classifier (L4.4) | P0 | The one gap in the worker.
A6 | Design backlog | Postgres + Cosmos schemas (L6.1/L6.2) | P0 | Tables + WORM.
A7 | Design backlog | Run Broker API surface (L4.2) | P0 | Worker's only CP door.
A8 | Design backlog | intake spec (L1.2) | P0 | Finish the Entry lane.
A9 | Design backlog | Validator re-prove mechanics (L5.5) | P0 | How a finding is proven.
A10 | Design backlog | Egress-gateway mechanics + SSRF callback (L7.1/L7.5) | P0/P1 | The one door + OOB.
A11 | Design backlog | Kill-switch propagation to live worker (L8.6) | P0 | Cancel must stop the worker.
A12 | Design backlog | Cred-vendor + lease-controller specs (L5.2/L5.3) | P0 | FID creds + dead-man.
B / D-2 | Decision (MD) | Network segmentation for dev/test/UAT | P0 | BLOCKED — load-bearing.
B / D-8 | Decision (MD) | Break-glass — none or override | P0 | Needs MD.
B / D-12 | Decision (MD) | POC success bar (N proven, cost/finding) | P0 | Needs MD.
C / AI-1 | Research | Agentic tooling landscape → action-classed tool registry | P1 | ADK native + MCP + custom.
C / AI-2 | Research | Interactive-run isolation (long session ≠ throwaway VM) | P1 | Fit the containment story.
C / AI-3 | Research | XBOW capability inventory → AEGIS parity matrix | P1 | Legitimate sources only (done first pass).
C / AI-4 | Research | Self-hosted ops-readiness checklist (XBOW issue categories) | P1 | Get ahead of failure modes.
AI-5 | Quantify (MD/platform) | Define the INPUTS + inbound volume (what feeds AEGIS, from where, how many) | P0 | See tab 17. Sizes the front door.
AI-6 | Quantify (MD/platform) | Define the OUTPUTS + their contracts + consumers | P0 | See tab 17. Verdict/result/report/events.
AI-7 | Quantify (MD/platform) | Size the TOTAL VOLUME the system handles (cases, runs, actions, model calls, evidence) | P0 | See tab 17. Drives capacity + cost.
AI-8 | Quantify (MD/platform) | Define the SCALING model + limits (concurrency ceiling, per-zone caps, fleet) | P0 | See tab 17. Ties to INF-18 / NFR-4.
AI-9 | Quantify (MD/platform) | Define MEASURABLE SUCCESS — pin FP<1%, N proven, cost/finding, MTTX, coverage%, chain depth, attribution | P0 | See tab 17. Closes D-12.
D-in-1 | Input (you) | The 3 starred MD questions — exact text | P0 | Blocking.
D-in-2 | Input (you) | Break-glass call | P0 | Blocking D-8.
D-in-3 | Input (you) | Business-case volumes & cost/finding | P0 | Closes D-12.
D-in-4 | Input (you) | Mobius input-vs-output + naming confirmations | P1 | D-11.
ADOPT-1 | XBOW adopt | Coverage map (endpoint × attackType, 4-state) | P1 | New capability.
ADOPT-2 | XBOW adopt | Adversarial FP cascade + FP-family taxonomy + voting | P1 | Strengthen Validator.
ADOPT-3 | XBOW adopt | Store a re-runnable, self-verifying PoC artifact on the finding | P1 | Evidence model.
ADOPT-4 | XBOW adopt | Per-call model budgets + prompt elision | P1 | model-port.
ADOPT-5 | XBOW adopt | Signed anti-scope-drift prefix on egress | P1 | egress-gateway.
ADOPT-6 | XBOW adopt | Agent back-off message on rate-limit | P1 | coordinator/egress.
ADOPT-7 | XBOW adopt | Track model_refusal as an operational friction | P1 | observability.
ADOPT-8 | XBOW adopt | Import the 51-subtype friction taxonomy | P1 | resilience + ops-readiness.

## 13. AWS Infrastructure
AWS Infrastructure & Needs
The AWS services, network tiers, and infrastructure AEGIS needs. Reuse where the platform already provides it; new under AEGIS's own dedicated account.
ID | AWS service / resource | Layer | Purpose in AEGIS | Config / needs
INF-01 | AWS Account (dedicated, isolated) | Boundary | Dedicated isolation boundary — AEGIS operated separately from Foundation. | Own account + SCPs (guardrails); no shared blast radius. Region: us-east-1 (confirm).
INF-02 | VPC — multi-tier | Network | Segmented network: entry / control-plane / task (runtime) / egress tiers. | Private subnets; the task (worker) tier has NO direct internet route.
INF-03 | AWS Fargate (ECS) | Compute | Runs the per-run worker as a Firecracker microVM (managed). | microVM-grade isolation without managing hosts (DEC-5).
INF-04 | Firecracker microVM | Compute/Isolation | The hypervisor boundary for exploit-code execution. | Baseline isolation; gVisor = fallback; udocker = packaging only.
INF-05 | ECS/EKS (control plane) | Compute | Hosts the deterministic control-plane + edge services. | Fargate or EKS; the CP is separate from the task tier.
INF-06 | ALB + Route 53 + ACM | Ingress | TLS front door for console-api / internal callers. | Internal ALB; mTLS; not a public internet edge (internal callers).
INF-07 | Egress-gateway (proxy + NAT) | Egress | The single scoped exit to targets — URL/DNS scope + per-target rate limit. | Forward proxy; the ONLY outbound route from the task tier to targets.
INF-08 | PrivateLink → Bedrock (Mantle) | Model access | In-perimeter model inference; no public internet to models. | Interface endpoint; AssumeRole per region for Claude-on-Bedrock.
INF-09 | IAM + STS (per-run FID) | Identity | Least-privilege per-run workload identity via AssumeRole. | Short-lived, scoped creds from cred-vendor; SID→FID; no standing perms.
INF-10 | KMS | Security | Encryption at rest for state / evidence; key isolation per data class. | CMKs; WORM evidence keys separated.
INF-11 | Secrets Manager / SSM Parameter Store | Security | Short-lived FID creds + config injection. | No standing secrets baked into the worker image.
INF-12 | Foundation Postgres (RDS/Aurora) — reuse | Data | State store: case / run / lease / idempotency. | Reused on the Foundation side; no new DB for AEGIS.
INF-13 | S3 + Iceberg / Glue (Cosmos) — reuse | Data | WORM findings / evidence / audit. | S3 Object-Lock (WORM); Iceberg tables; hash-chained; pointer-only.
INF-14 | MSK / Kafka (Portico) — reuse | Eventing | Event backbone — intake + run/agent/findings/audit events. | Reused; transactional outbox for reliable emit; DLQ.
INF-15 | CloudTrail + CloudWatch (+ SIEM) | Observability | Audit trail + metrics/logs; attribution (identity rail). | SID/FID on every action; trace/correlation-id; export to SIEM.
INF-16 | Security Groups / NACLs | Network security | Micro-segmentation; the worker has exactly 2 outbound paths. | Worker → Run Broker (CP) + Egress-gateway (targets); no inbound.
INF-17 | ECR / Artifactory | Images | Golden pentest base image; fork per sandbox. | Rootless image; signed; vulnerability-scanned.
INF-18 | Auto Scaling | Capacity | Scale the worker fleet to run demand; enforce a concurrency ceiling. | Platform-wide worker-microVM cap = the cost/capacity guardrail.
INF-19 | VPC Endpoints (interface/gateway) | Network | Private access to S3 / Bedrock / Secrets / STS without a NAT. | Keeps AWS-API traffic off the internet.
INF-20 | Twin / replica environment | Targets | Zone B destructive (DESTROY-class) testing on an isolated replica. | Provisioned per target class (D-10); how = TBD.
INF-21 | OOB / OAST listener | Targets | In-scope callback endpoint for SSRF / blind-vuln verification. | NEW (L7.5); governed + in-scope, not an open hole.
INF-22 | TLS + platform LB (front) | Ingress | Minimal front protection for internal callers. | WAF/DDoS framing dropped (internal, not public edge).
Capacity & non-functional needs (to size with the platform team)
• Per-run worker sizing (vCPU / memory / disk) — set from baseline case profiles; [TBD].
• Concurrency: baseline sweeps run many targets at once → a platform-wide microVM ceiling (cost guardrail).
• Zone concurrency limits: canary (C)=1, replica (B)=small N, read-only-prod (A)=capped.
• Multi-AZ for control-plane + data; the per-run worker is disposable (no DR needed).
• Region: us-east-1 (confirm); data residency per firm policy.
• Network: task tier egress ONLY via the egress-gateway; AWS-API access via VPC endpoints.
• Cost: per-run budget (token/time/action) + the fleet ceiling; feeds cost-per-proven-finding.

## 14. Business Outcomes
Business Outcomes
The value AEGIS delivers to the business, each with the metric that proves it. (Requirements are HOW; outcomes are WHY.)
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Outcome | Description | Metric / KPI | Target | Comments
BO-1 | Governed offensive capability kept in-house | Build vs buy/cede — retain the capability AND its governance under firm control. | Strategic (capability retained) | yes
BO-2 | Continuous, automated exploitability validation at scale | Baseline sweeps run on every in-scope target, concurrently, on a cadence. | Targets swept / month | ramp to full estate
BO-3 | Lower cost per proven finding | Automated proof replaces manual pentest hours for the repeatable work. | Cost / proven finding | ↓ vs manual [TBD]
BO-4 | High precision — few false positives | Refute-by-default validation → less wasted remediation effort. | False-positive rate | < 1%
BO-5 | Faster time-to-verdict | Async fire-and-stream; a verdict in minutes, not weeks. | Mean time to exploitability (MTTX) | minutes
BO-6 | Regulated audit posture / full attribution | Every action tied to a named human (SID→FID); WORM tamper-evident evidence. | % actions attributable | 100%
BO-7 | Competitive edge vs XBOW | Broader attack surface + twin/replica re-prove + human↔agent attribution. | Capability lead | ahead on 3 axes
BO-8 | Higher coverage of flagged vulns proven | Continuous coverage measurement across the estate. | % flagged vulns proven | ↑ / continuous
BO-9 | Finds chained, multi-surface exploits | Chain depth > 1 — what single-surface scanners cannot do. | Chain depth | > 1
BO-10 | Safe scale-out of CyberOps | Governed playbooks (Plexus) — reviewed nodes only, no ungoverned steps. | Promoted playbooks | growing
BO-11 | Faster, cheaper build via reuse | Reuse Portico / Postgres / Cosmos / Bedrock — no new infra to build or run. | Build cost / time | ↓
BO-12 | Better enterprise risk decisioning | Verdicts feed the VM Risk Score / Mobius. | Verdicts → risk score | integrated

## 15. Requirements (FR-NFR)
Requirements — Functional & Non-Functional
FR = what the system must DO. NFR = how WELL it must do it. (Business-level asks are in the BRD tab; these are the buildable requirements.)
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Type | Requirement | Pri | Comments
FR-1 | Functional | Ingest exploitability requests from machines (Portico) and run requests from humans (console-api). | P0
FR-2 | Functional | Validate + normalize each request into a canonical Case; dedup duplicates. | P0
FR-3 | Functional | Plan the run and spawn a governed, disposable per-run worker. | P0
FR-4 | Functional | Execute action-classed steps (READ/CHANGE/DESTROY) with per-action authorization. | P0
FR-5 | Functional | Write model-generated exploit code into an isolated microVM and run it there. | P0
FR-6 | Functional | Re-prove findings up the confidence ladder; only the Validator writes findings. | P0
FR-7 | Functional | Stream live run progress over SSE and allow status polling. | P0
FR-8 | Functional | Cancel a run — the kill switch must reach a live worker, not just the DB. | P0
FR-9 | Functional | Persist findings/evidence to WORM (Cosmos) and run state to Postgres. | P0
FR-10 | Functional | Return an ExploitabilityResult and feed the VM Risk Score / Mobius. | P0
FR-11 | Functional | Support baseline (headless) and interactive (human-steered) run modes. | P1
FR-12 | Functional | Enforce Rules of Engagement and prod-safe zones A/B/C. | P0
FR-13 | Functional | Produce a coverage map (endpoint × attackType) and a report. | P1
FR-14 | Functional | Support contained malware detonation/analysis — twin only, never generation. | P1
NFR-1 | Non-functional · Security | Hypervisor isolation (Firecracker microVM); external governance; no standing secrets in the worker. | P0
NFR-2 | Non-functional · Auditability | WORM, hash-chained evidence; full SID→FID attribution on every action. | P0
NFR-3 | Non-functional · Availability/DR | Multi-AZ control plane + data; DR to a second region (us-west-2) on switchover. | P1
NFR-4 | Non-functional · Scalability | Scale the worker fleet to demand; enforce a platform-wide concurrency ceiling. | P0
NFR-5 | Non-functional · Performance | Async fire-and-stream; never block for a verdict; MTTX in minutes. | P0
NFR-6 | Non-functional · Reliability | Idempotency, transactional outbox, DLQ/retry, circuit breakers, backpressure. | P1
NFR-7 | Non-functional · Cost | Per-run budget enforcement (token/time/action); track cost per proven finding. | P1
NFR-8 | Non-functional · Compliance | Standards backbone: PTES/OWASP/NIST 800-115/MITRE ATT&CK+ATLAS/DORA/PCI 11.4. | P0
NFR-9 | Non-functional · Observability | Trace/correlation-id request→run→action; metrics/SLOs; model_refusal tracked. | P1
NFR-10 | Non-functional · Maintainability | Reuse platform substrates; worker = a harness configured on ADK, not a rebuilt loop. | P1
NFR-11 | Non-functional · Least privilege | Per-run FID via STS; short-lived scoped creds; worker has exactly 2 outbound paths. | P0
NFR-12 | Non-functional · Data residency | Region us-east-1 (confirm); data handling per firm policy. | P1

## 16. Architecture Choices
Architecture Choices (ADR summary)
Each key design choice: the options weighed, what was chosen, why, and the trade-off. Ties to the locked decisions (DEC-*) in the Decisions tab.
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | Choice area | Options considered | Chosen | Rationale | Trade-off / note | Comments
AC-1 | Build vs buy vs cede | (a) governed in-house build · (b) buy a vendor · (c) don't do it | (a) in-house build | Retain the capability and its governance; a vendor is a black box (see XBOW staff-only debug). | Higher build effort; owned roadmap.
AC-2 | Worker isolation | Docker (shared kernel) · gVisor · Firecracker microVM | Firecracker microVM (via Fargate) | The worker runs exploit code → needs a hypervisor boundary, not a shared kernel. | Slightly heavier than containers; managed by Fargate.
AC-3 | Governance placement | In-process guardrail · external authorization wall | External (via Run Broker) | A compromised agent can't bypass/forge/silence its own guard; containment is structural. | One more network hop per action.
AC-4 | Event backbone | New Kafka/Pulsar · reuse Portico (Kafka/MSK) | Reuse Portico (Amazon MSK) | No new bus to run; the firm's platform already provides it. | Idempotency still needs app-level dedup, not Kafka EOS.
AC-5 | Orchestration | Saga engine · Kestra per-run · own thin orchestrator | Own per-run orchestrator; Kestra = trigger only | Kestra can't be created per run; orchestration is our WHAT/HOW, Kestra is the WHEN. | We own the orchestrator code.
AC-6 | Agent framework | Strands · raw Anthropic SDK · Smart SDK over Google ADK | Smart SDK over Google ADK | Firm standard; ADK Runner IS the loop → we configure a harness, not build one. | ADK is Gemini-native; Bedrock via LiteLlm adapter.
AC-7 | Model access | Direct internet · Bedrock via PrivateLink (Mantle) | Bedrock via PrivateLink (Mantle) | In-perimeter, no public internet to models. | Firm-proxy request/rate limits to handle gracefully.
AC-8 | Edge design | One 'aegis-api' · two edges by caller type | Two edges — console-api (humans) + intake (machines) | Human REST+SSE and machine events have different auth/shape/failure modes. | Two services to run (both thin/stateless).
AC-9 | Compute platform (CP/edges) | ECS Fargate · EKS | ECS Fargate (EKS optional) | Matches the worker's Fargate; less to operate. EKS if the platform standardizes on K8s. | Open decision — pick per platform standard.
AC-10 | Run model | Blocking wait-for-verdict · async fire-and-stream | Async fire-and-stream (202 + run_id) | Runs take minutes-to-hours; a blocking call dies on any network blip. | Client must stream/poll.
AC-11 | Live stream transport | WebSocket · Server-Sent Events (SSE) | SSE now; WebSocket when interactive lands | Progress is one-directional; SSE is one GET, proxy-friendly, auto-reconnecting. | Bidirectional steering needs WS later.
AC-12 | State stores | New DB + Redis · reuse Postgres + Cosmos WORM | Reuse Foundation Postgres + Cosmos (S3/Iceberg WORM) | No new datastore; WORM gives tamper-evident audit. | Depends on Foundation availability.
AC-13 | Proxies | Single proxy · 2 reverse (ALB, Run Broker) + 1 forward (egress) | Two reverse proxies + one forward proxy | Front-end LB, single audited CP door, and a scoped outbound door are distinct concerns. | Three components to run.
AC-14 | Worker code execution | Built-in Google/Gemini sandbox · custom ADK BaseCodeExecutor | Custom BaseCodeExecutor → ship code into the microVM | Google's sandboxes are locked down and can't reach internal targets. | We own the executor + guest agent.
AC-15 | Network tiering | Flat VPC · front-end/back-end/task-isolated/egress/data subnets | Five-tier subnet separation | Task tier isolated (no internet route); egress is the only outbound door. | More subnets/route tables to manage.
AC-16 | Resilience / DR | Single region · multi-region DR (us-east-1 ↔ us-west-2) | Multi-region DR (planned) | Regulated availability; matches firm house pattern (cross-region replication). | DR infra provisioned on switchover — cost.
AC-17 | Findings authority | Any agent can record · only the Validator writes | Only the Validator writes findings (refute-by-default) | Independent adjudication; the agent proposes, the Validator proves. | Adds a validation stage per finding.
AC-18 | Idempotency | Rely on Kafka exactly-once · app-level dedup key in Postgres | App-level dedup key in Postgres | Kafka EOS only holds inside Kafka; the side effect (start a run) needs its own key. | 24h TTL key store.

## 17. Volume & Success
Volume & Success
Inputs, outputs, total volume, scaling, and the definition of success. [TBD] = a number the MD / platform team owes (AI-5…AI-9).
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
1 · Inputs — what feeds AEGIS
Input | Source | What it is | Est. volume | Contract / notes
Machine exploitability request | Foundation (CTC/VINES) via Portico | A flagged vuln to prove exploitable on a target (the headless ExploitabilityRequest). | [TBD] / month | 1 request → 1+ Case; idempotent on event id.
Human run request | Pentester / CyberOps via console-api | An interactive or on-demand run (ad-hoc exploit, targeted test). | [TBD] / month | OBO SID; Idempotency-Key required.
Scheduled sweep trigger | Kestra | Cadence fire that launches baseline runs across the in-scope estate. | [TBD] cadence | The WHEN; fans out to many targets.
New-package event | SDLC → BB / Artifactory → Portico | A new/changed package that warrants a fresh exploitability check. | [TBD] / month | Feeds the baseline population.
Target inventory / RoE | Scope + asset ownership | The in-scope targets and their Rules of Engagement. | [TBD] targets | Admission needs a valid RoE.
Interactive steer (mid-run) | Human (HITL) | Live instructions to push a run harder. | ad-hoc | SSE now; WS when interactive lands.
2 · Outputs — what AEGIS produces
Output | Consumer | What it is | Contract / notes
Exploitability verdict | VM Ops / Mobius (VM Risk Score) | proven-exploitable / not / ambiguous, with confidence rung. | ExploitabilityResult contract.
Finding + re-runnable PoC | Cosmos (WORM) + report | The proven finding, evidence, and a self-verifying PoC artifact. | Validator-written only; hash-chained.
Run report | Human console / report doc | Exec summary, methodology, coverage, states (XBOW-parity schema). | Pointer-only to WORM evidence.
Coverage map | Result + console | endpoint × attackType, 4-state (XBOW learning). | Adopt item ADOPT-1.
Live run stream | Human console | SSE progress events (plan→act→observe→propose). | Last-Event-ID reconnect.
Domain events | Portico (run.*, agent.*, findings.*, audit.*) | Facts other systems subscribe to. | Transactional outbox; DLQ.
Audit trail | Cosmos (WORM) + CloudTrail/SIEM | Every action, SID→FID attributed. | 100% attributable (NFR-2).
3 · Total volume the system handles
Dimension | Estimate | Notes
Cases / month | [TBD] | Distinct exploitability questions (dedup'd).
Runs / month | [TBD] | Attempts, incl. retries + interactive (≥ Cases).
Concurrent runs (peak) | [TBD] | Sets the worker-fleet size + concurrency ceiling.
Actions / run | [TBD] | Authorize()-gated steps — governance call volume.
Model calls / run | [TBD] | Drives model-port budget + Bedrock cost.
Evidence volume / month | [TBD] | WORM growth in Cosmos (S3/Iceberg).
Targets in scope | [TBD] | The estate baseline sweeps must cover.
Coverage target | [TBD] % of flagged vulns proven | The continuity KPI (BO-8).
4 · Scaling model + limits
Dimension | Approach | Limit / target
Worker fleet | Auto-scale disposable Firecracker microVMs (Fargate) to run demand. | Platform-wide microVM ceiling = cost/capacity guardrail (INF-18).
Concurrency ceiling | Cap total concurrent runs platform-wide. | [TBD] — the load/cost guardrail (NFR-4).
Per-zone caps | Canary (C)=1 · replica (B)=small N · read-only prod (A)=capped. | Safety-driven, not just cost.
Per-target rate | Coordinator + egress-gateway throttle per target+env. | Collision avoidance across concurrent runs.
Edge throttle | Per-SID rate limit at console-api. | Layer 1 of the 2-layer rate policy (DEC-12).
Model throughput | Per-call budgets + prompt elision + fallback. | Handle firm-proxy request/rate limits gracefully.
Control plane / data | Multi-AZ; DR to us-west-2 on switchover. | Worker is disposable (no worker DR needed).
Horizontal services | Edges + CP services scale out (stateless). | Fargate/EKS; no sticky state.
5 · Measurable success — the definition of done
Metric | Definition | Target
False-positive rate | Proven findings that survive refute-by-default validation. | < 1% (hard gate, BO-4 / D-12).
N proven findings | Count of true exploitable findings in the POC window. | [TBD] — MD to set (BR-9).
Cost per proven finding | Total run cost ÷ proven findings. | ≤ [TBD] — MD to set; ↓ vs manual.
Mean time to verdict (MTTX) | Request → exploitability verdict. | [TBD] minutes (BO-5).
Coverage % | Flagged vulns proven ÷ flagged vulns, over the estate. | ↑ / continuous (BO-8).
Chain depth | Multi-surface chains proven (web→cloud→role→data). | > 1 (BO-9).
Attribution | Actions tied to a named human (SID→FID). | 100% (BO-6 / NFR-2).
Targets swept / month | In-scope targets baseline-swept on cadence. | [TBD] → ramp to full estate (BO-2).
Success in one line: a proven-exploitable verdict, with re-runnable proof and full attribution, at < 1% false positives — faster and cheaper than a human doing it by hand, across a growing share of the estate.

## 18. POC Plan
POC Plan — the POCs to be done
The three MD-framed directions (build pipeline · sandbox · on-prem) written out as runnable POCs, plus one stretch chain POC. Success bar ties to D-12 (FP < 1%, N proven [TBD], cost/finding [TBD]).
WHAT WE AUTOMATE — the EXPLOITABILITY VERDICT: “is this flagged vulnerability actually exploitable on this target, in this environment — and prove it?” That is the pentester’s core judgment, done by hand today. Humans keep: run approval (RoE), the final clear/sign-off, DESTROY-class calls, and novel-exploit synthesis (gated).
ID | POC | What it proves (objective) | Minimal scope to run it | Success criteria | Depends on / blockers | Comments
POC-1 | Build-pipeline POC | A new/changed package flows SDLC → event bus → scheduler → sandbox and launches a GOVERNED run with no manual step. | One package, one trigger path; a stubbed one-action run is fine. | A run is created with a run_id, attributed (SID→FID), under a valid RoE — end to end, hands-off. | Event-bus contract (A3), intake spec (A8).
POC-2 | Sandbox POC (the core one) | The exploitability verdict, end to end: take one flagged vuln on one target and PROVE exploitable / not, with evidence, inside the microVM, out through the egress-gateway, every action authorized. | One target + one vuln class (e.g. a web IDOR on a replica); baseline (headless) mode. | ≥ 1 proven finding with a re-runnable PoC · false-positive rate < 1% on the slice · 100% of actions authorized + attributed · verdict returned. | Governance authorize() (A1 ✓ specced), worker (prototyped), egress-gateway (A10), Validator (A9).
POC-3 | On-prem / model-posture POC | The model + runtime posture works in-perimeter: in-VPC model access (PrivateLink) meets latency/cost/perimeter needs; an on-prem/hybrid fallback is evaluated. | The Sandbox POC’s run, but measuring model latency, per-run cost, and perimeter compliance; plus a paper/lab check of on-prem. | A run completes using in-perimeter models within acceptable latency + per-run cost · on-prem option assessed with a go/no-go. | Model-port + proxy-limit handling (L4.5), PrivateLink to the model gateway.
POC-4 | Cross-surface chain POC (stretch) | The differentiator: chain across surfaces — e.g. web SSRF → cloud metadata → assumed role — something a single-surface scanner cannot produce. | One planned chain on a replica/twin; Zone B, human-approved. | A chain of depth > 1 proven on the twin, with the full path captured as evidence. | Depends on POC-2 first; twin/replica provisioning (D-10).

## 19. Design Review
Design Review — architecture findings
Independent review of the AEGIS design. Each row: the issue, why it matters, the recommendation, and priority. The safety spine is sound; these tighten the data spine, the governance throughput/availability model, and measurement.
ID | Finding | Issue — why it matters | Recommendation | Pri | Comments
DR-01 | Governance hot-path & availability | authorize() runs on every action, synchronous and fail-closed, so governance uptime equals platform uptime. A long run is thousands of actions; many concurrent runs multiply the load on one service that must never fail open. | Split the decision by danger class: READ checks can use a locally cached, read-only scope snapshot (sidecar); CHANGE / DESTROY / UNKNOWN always go central. Lease read-class authority per run instead of a central token per packet. | P0
DR-02 | Case model is the unspecced keystone | The two edges, the governance wall and the worker are specced, but the Case model (L2.2) they all reference is still named only. The RoE schema, the dedup fingerprint and the Case-vs-Run lifecycle are undefined. | Spec the Case model next, ahead of other P0 items. Pin the RoE schema, define the dedup fingerprint (what makes two requests the same Case) and the Case/Run lifecycle rules. | P0
DR-03 | Action classifier is defense-in-depth, not the boundary | The classifier (L4.4) is a stub, which reads as a hole. The real boundary is the network topology: the worker can only leave through the two doors and the egress-gateway enforces scope regardless of intent. | State plainly that the topology is the containment wall and the classifier is telemetry plus CHANGE-routing. Name the residual risk: a mis-classified CHANGE waved through as READ could mutate an in-scope target without the central check. | P1
DR-04 | Kill-switch already has a containment floor | L8.6 (kill reaching a live worker) is flagged P0 unsolved, which looks scarier than it is. The short capability-token TTL already caps how long a killed run can keep acting, because it cannot mint the next token. | Frame token expiry as the guaranteed containment bound (exists today by construction); treat an active kill channel (guest-agent poll or microVM teardown) as a best-effort speed-up, not a blocker to running safely. | P1
DR-05 | Eval harness gates the business case — move it earlier | The value proposition (false-positive rate under 1%, cost per proven finding) cannot be claimed without an eval harness and a ground-truth lab-target corpus, yet that work is parked in P1. | Promote the eval harness to a P0 companion of the Sandbox POC. Build the measuring instrument before the POC that is supposed to produce the number. | P0
DR-06 | Callback listener is a genuine tension with no-inbound | Proving blind server-side request issues needs the target to reach back to a listener, which is an inbound path receiving outside input, in a design whose story is no-inbound plus two outbound doors. | Give the callback listener its own mini-design: isolated, in-scope-only, correlates hits to a run, its own tiny blast-radius zone with no path to the control plane. Do not let it become a quiet exception to the isolation model. | P1
DR-07 | Interactive runs break the disposable-worker model | Baseline is a throwaway microVM per run. Interactive is a human steering for hours, a long-lived session with a different isolation shape (flagged as AI-2). | Keep interactive inside a microVM with a hard max-lease and checkpointing, and treat the human as another attributed action source that still passes through authorize(). More privilege, never a bypass of the wall. | P1
DR-08 | Evidence needs confidentiality, not just tamper-evidence | WORM gives integrity (findings cannot be altered) but the design is silent on who may read the evidence store, which holds sensitive step-by-step detail and possibly sensitive target data. | Add an access model for the findings/evidence store: read authorization, and minimization or redaction of sensitive target data. An auditor will ask who can read it, not just whether it can be changed. | P1