## Overview
Exploitation Sandbox (VM) — Q4 Tracker
Harness → service POC, built in the isolated env. Downstream of CRAFT. Oct–Dec 2026.
THE PLAN IN ONE LOOK
The work | Convert the existing agent harness into a callable service, built in the isolated environment where the harness already lives (fastest path — nothing new to stand up). This is the sandbox downstream of the CRAFT code scanner: it receives exploitation requests and runs the exploit code inside its own isolation boundary.
Shape of Q4 | Oct: secure model access, stand up the POC, begin the harness→service conversion. Oct–Nov: one engineer builds and proves it; the operating-model + isolation design wraps in parallel. Dec: demo with real CyberOps requests, then freeze the design and start development.
Staffing | ~1 engineer carries the conversion for two months. Lead drives the design + stakeholders and stays close enough to cover the engineer.
↔ Paired with the Pen-Testing tracker. They're separate works, but the pen-testing pipeline runs its exploits inside THIS sandbox — so this one is the shared dependency.
PROGRESS (live — updates as you set Status on the Tasks tab)
Metric | Count
Total tasks | 14
Done | 0
In Progress | 0
Blocked | 1
Not Started | 13
% complete | 0%
HOW TO USE
• Tabs: Tasks (weekly working list) · Milestones & Gates (dates + what 'done' means) · Risks & Dependencies.
• Set Status on Tasks with the dropdown — the Progress box recalculates automatically. Pick from the list, don't type.
• Owners are roles: Lead = you · Engineer = the POC engineer · Principal / Architect = senior design partners · Product · CyberOps · Sponsor (MD).
• Dates are a working draft — drag to your real calendar. The Oct / Oct–Nov / Dec phase buckets hold even if exact days move.

## Tasks
Tasks
The working list — update Status weekly.
ID | Track | Phase | Task | Owner (role) | Start | Due | Priority | Status | Depends On | Notes
S1 | Sandbox | Oct | Secure DEV model access (in-perimeter inference for the desired model) | Lead | 2026-10-01 | 2026-10-07 | Critical | Blocked | — | Day-1 blocker. The harness assembles without it, but the model-driven loop can't run until this lands. Make it the very first task, before any code.
S2 | Sandbox | Oct | Define POC success criteria (the acceptance test) | Lead | 2026-10-01 | 2026-10-10 | High | Not Started | — | Write it now so December's freeze has something to measure: request in → classify → authorize() passes → exploit runs in sandbox → result returns → stays in bounds. Demo must also show it REFUSING an out-of-bounds action.
S3 | Sandbox | Oct | Define the upstream exploitation-request contract (the interface) | Lead | 2026-10-06 | 2026-10-17 | High | Not Started | S2 | First-mover advantage: you set the request shape, so upstream (incl. Foundation) builds to your interface later instead of the reverse.
S4 | Sandbox | Oct | Collect 2–3 representative exploitation-request samples from CyberOps | Lead, CyberOps | 2026-10-06 | 2026-10-31 | High | Not Started | S3 | Needed to run the Dec demo against something real. Don't let December be the first time you see an actual request.
S5 | Sandbox | Oct | Stand up the POC in the existing isolated environment | Engineer | 2026-10-08 | 2026-10-17 | High | Not Started | S1 | Same env the harness already lives in = fastest path, no new setup to prove it out.
S6 | Sandbox | Oct–Nov | Convert harness → agentic service (swap the stubbed model seam for the real one; wire the desired model) | Engineer | 2026-10-15 | 2026-11-21 | Critical | Not Started | S1, S5 | The core POC work. Replace the mock behind the existing interface with the live model — same seam, real dependency.
S7 | Sandbox | Nov | Run the model-driven loop end-to-end on one narrow slice | Engineer | 2026-11-10 | 2026-11-28 | High | Not Started | S6 | One engine / one app / one vuln type. Local executor first, then the microVM boundary.
S8 | Sandbox | Nov | Harden & document the seams so a 2nd engineer could pick it up cold | Engineer | 2026-11-17 | 2026-11-28 | Medium | Not Started | S6 | Single-engineer risk hedge — keep the POC handoff-ready.
S9 | Sandbox | Oct–Nov | Design the operating model + isolation boundary + Foundation→sandbox handoff | Lead, team | 2026-10-01 | 2026-11-28 | High | Not Started | — | The design MD wants cracked: repo + version control + Dev/UAT/Prod for TWO populations (platform owns the stable baseline that runs by default; cyber-ops write ad-hoc exploit code, raise PRs, run concurrently on the same target, promote good code into baseline). Its own isolation boundary, operated separately from Foundation. Runs in PARALLEL with the build.
S10 | Sandbox | Dec | Demo: feed CyberOps' real requests; show it running AND refusing out-of-bounds | Lead, Engineer | 2026-12-01 | 2026-12-12 | Critical | Not Started | S4, S7, S9 | The Q4 proof point. The 'it can't misbehave' moment is what sponsors need before greenlighting anything near prod.
S11 | Sandbox | Dec | Go/No-Go gate → freeze sandbox design, start development | Lead, Sponsor, Product | 2026-12-12 | 2026-12-19 | Critical | Not Started | S10 | The decision gate. The sandbox env then doubles as the build/test bed; migrate in-house later once trusted.
S12 | Sandbox | Dec | Use the demo as the case for Q1 headcount (1 engineer → squad) | Lead | 2026-12-12 | 2026-12-19 | Medium | Not Started | S10 | Convert a win straight into people instead of losing momentum.
S13 | Program | Oct | Give Product the sandbox Q4 plan (one-pager) | Lead | 2026-10-01 | 2026-10-07 | High | Not Started | — | Answers the 'what's your Q4 plan?' ask for this track and shows you driving, not catching up.
S14 | Program | Ongoing | Weekly status update rhythm (sandbox) | Lead | 2026-10-01 | 2026-12-19 | Medium | Not Started | — | Keep stakeholders aligned and momentum visible.

## Milestones & Gates
Milestones & Gates
The dates that matter and the bar each one has to clear.
ID | Milestone | Target | Exit criteria (what 'done' means) | Status
M1 | Model access in hand (DEV) | 2026-10-07 | Desired model reachable from the isolated env; the harness can call it. | Not Started
M2 | Sandbox Q4 plan delivered to Product | 2026-10-07 | One-pager shared; Product aligned on the phased plan (design-proven-ready, not production). | Not Started
M3 | Request contract + samples locked | 2026-10-31 | Interface defined; 2–3 real CyberOps request samples in hand to test against. | Not Started
M4 | Harness converted to a service | 2026-11-21 | Live model wired behind the interface; the service is callable and runs the loop. | Not Started
M5 | Sandbox design complete | 2026-11-28 | Operating model (two populations), isolation boundary, and Foundation→sandbox handoff all designed. | Not Started
M6 | Sandbox POC demo | 2026-12-12 | Real requests run end-to-end in the sandbox AND an out-of-bounds action is shown being refused. | Not Started
M7 | Q4 close — Go/No-Go gate | 2026-12-19 | Decision made: freeze design + start development; Q1 headcount case put forward. | Not Started

## Risks & Dependencies
Risks & Dependencies
The handful of things most likely to knock this track off course — and what to do.
ID | Item | Type | Impact | Mitigation / action | Owner | Status
R1 | Model access is the gating dependency for the whole POC | Blocker | High | Make it task #1 (S1); escalate early if provisioning is slow. Harness work proceeds in parallel, but the loop can't close without it. | Lead | Open
R2 | "It works" is undefined, so the Dec freeze has nothing firm to decide on | Risk | High | Write the acceptance test now (S2). Make the demo show BOTH a successful run and a refused out-of-bounds action. | Lead | Open
R3 | CyberOps request samples arrive too late to test against | Dependency | High | Pull 2–3 samples by end of Oct (S4). Don't let December be the first real request you see. | Lead, CyberOps | Open
R4 | One engineer for 2 months = single point of failure | Risk | Medium | Keep seams documented and handoff-ready (S8); Lead stays close enough to cover a gap. Confirm the engineer already knows the harness/SDK, or budget ramp time. | Lead | Open
R5 | Isolation boundary not ready when the build needs it | Dependency | Medium | Sequence the isolation-boundary design early in S9; confirm the separate boundary can be stood up in the existing env. | Lead | Open
R6 | Upstream / Foundation hasn't built their side yet | Dependency | Medium | Keep moving independently; define the request interface (S3) so they build to yours later. Being first is leverage — use it. | Lead | Open