## Overview
Pen Testing — Q4 Tracker
Automated pen-testing platform: request in → pipeline → report out. Design-heavy, needs a UI. Oct–Dec 2026.
THE PLAN IN ONE LOOK
The work | The broader automated pen-testing platform: an exploitation/test request comes IN from upstream, the pipeline runs, and a reconciliation report goes OUT downstream to the product's engineering team. It needs a UI and the full feature set, so it earns its own longer timeline.
Shape of Q4 | Oct–Nov: design + requirements with the full team — pull everything already captured into one coherent design (upstream in, reporting out, all requirements), plus UI/UX. Dec: freeze only the thin first slice, launch the testing POC, start the build.
Staffing | Lead + Principal + Architect + team on the design, in parallel with the sandbox POC. Onboard newcomers via the existing design docs so they self-serve instead of pulling the design out of the Lead live.
↔ Paired with the Exploitation Sandbox tracker. This pipeline runs its exploits inside that sandbox — so the sandbox is a dependency for this track's POC.
PROGRESS (live — updates as you set Status on the Tasks tab)
Metric | Count
Total tasks | 11
Done | 0
In Progress | 0
Blocked | 0
Not Started | 11
% complete | 0%
HOW TO USE
• Tabs: Tasks (weekly working list) · Milestones & Gates (dates + what 'done' means) · Risks & Dependencies.
• Set Status on Tasks with the dropdown — the Progress box recalculates automatically. Pick from the list, don't type.
• Owners are roles: Lead = you · Principal / Architect = senior design partners · team = your engineers · Product · CyberOps · Sponsor (MD).
• Dates are a working draft — drag to your real calendar. The Oct / Oct–Nov / Dec phase buckets hold even if exact days move.

## Tasks
Tasks
The working list — update Status weekly.
ID | Track | Phase | Task | Owner (role) | Start | Due | Priority | Status | Depends On | Notes
P1 | Pen Test | Oct–Nov | Formulate the full testing picture into one coherent design | Lead, Principal, Architect, team | 2026-10-01 | 2026-11-28 | High | Not Started | — | Lots already captured — this is organizing and completing it, not starting cold: upstream request IN, pipeline, reporting OUT, and all the requirements gathered so far.
P2 | Pen Test | Oct–Nov | Requirement gathering with CyberOps (testing track) | Lead, CyberOps | 2026-10-01 | 2026-11-21 | High | Not Started | — | Runs in parallel with the sandbox's requirements effort.
P3 | Pen Test | Oct | Onboard Principal + Architect via the existing design docs (self-serve) | Lead | 2026-10-01 | 2026-10-17 | High | Not Started | — | Point newcomers at the written design instead of re-explaining live — the single biggest protector of your velocity.
P4 | Pen Test | Oct | Design the upstream side: how a test/exploitation request comes IN | Lead, team | 2026-10-06 | 2026-10-31 | High | Not Started | P1 | The entry contract for the pipeline — what a request carries, how it's scoped and authorized.
P5 | Pen Test | Oct–Nov | Design the downstream side: the reporting OUT | Lead, team | 2026-10-20 | 2026-11-28 | High | Not Started | P1 | The reconciliation report to the product's engineering team — scanner-found vs independently-tested, and the overlap (confirmed). Needs a strong model to write clear dev guidance per bucket.
P6 | Pen Test | Oct–Nov | Design the thin first slice to actually build (NOT the whole product) | Lead, team | 2026-10-20 | 2026-11-28 | High | Not Started | P1 | Freeze only this in December; keep the rest as roadmap. Protects Oct–Nov from doing everything at once.
P7 | Pen Test | Oct–Nov | UI/UX design (the testing product needs a UI + full feature set) | Lead, team | 2026-10-20 | 2026-11-28 | Medium | Not Started | P1 | This is what makes Pen Testing a longer timeline than the sandbox. Sequence the UI design first, wire it to the API last.
P8 | Pen Test | Dec | Freeze the thin-slice design, launch the testing POC, start the build | Lead, team | 2026-12-01 | 2026-12-19 | High | Not Started | P6 | December exit. The POC runs its exploits in the exploitation sandbox (see that tracker).
P9 | Program | Oct | Give Product the pen-testing Q4 plan (one-pager) | Lead | 2026-10-01 | 2026-10-07 | High | Not Started | — | Answers the 'what's your Q4 plan?' ask for this track.
P10 | Program | Oct | Align with Product on naming the overall initiative | Lead, Product | 2026-10-01 | 2026-10-17 | Low | Not Started | — | Give Product clean language for the umbrella over both tracks (sandbox + pen testing) so the naming stops wobbling.
P11 | Program | Ongoing | Weekly status update rhythm (pen testing) | Lead | 2026-10-01 | 2026-12-19 | Medium | Not Started | — | Keep stakeholders aligned and momentum visible.

## Milestones & Gates
Milestones & Gates
The dates that matter and the bar each one has to clear.
ID | Milestone | Target | Exit criteria (what 'done' means) | Status
M1 | Pen-testing Q4 plan delivered to Product | 2026-10-07 | One-pager shared; Product aligned on the phased plan (design + thin-slice POC, not full product). | Not Started
M2 | Newcomers onboarded via the design docs | 2026-10-17 | Principal + Architect self-serving from the written design; Lead's maker-time reclaimed. | Not Started
M3 | CyberOps requirements gathered | 2026-11-21 | Testing-track requirements captured from CyberOps. | Not Started
M4 | Full testing design formulated | 2026-11-28 | Upstream-in, reporting-out, and all captured requirements pulled into one coherent design. | Not Started
M5 | Thin-slice + UI design done | 2026-11-28 | First build slice designed; UI/UX designed; the rest parked as roadmap. | Not Started
M6 | Q4 close — freeze + build start | 2026-12-19 | Thin slice frozen, testing POC up, build started (exploits running in the sandbox). | Not Started

## Risks & Dependencies
Risks & Dependencies
The handful of things most likely to knock this track off course — and what to do.
ID | Item | Type | Impact | Mitigation / action | Owner | Status
R1 | Over-scoping the full design into 8 weeks while the sandbox POC also runs | Risk | High | Freeze only the thin first slice (P6); keep the rest as roadmap. Design sprint one deeply, sketch the rest. | Lead | Open
R2 | CyberOps requirements arrive too late to shape the design | Dependency | High | Start requirement gathering day 1 (P2); don't wait for the sandbox effort to finish. | Lead, CyberOps | Open
R3 | Newcomers slow the Lead by extracting the design live | Risk | Medium | Onboard via the existing docs (P3); reserve maker-time for the design, not live storytelling. | Lead | Open
R4 | This track's POC depends on the exploitation sandbox being ready | Dependency | Medium | Track the sandbox's Dec readiness (other tracker); keep the thin slice small enough to run on the sandbox's first working path. | Lead | Open
R5 | The console/UI layer gets absorbed by another org | Risk | Medium | Keep the UI sequenced as this track's own layer (P7); frame the sandbox as infrastructure vs the console/workflow as this track's. Don't surface UI ownership proactively. | Lead | Open
R6 | Upstream / Foundation hasn't built their side yet | Dependency | Medium | Keep moving independently; define the upstream request contract (P4) so they build to yours later. | Lead | Open